## BLG448E_Final_Questions
Project Management in Engineering
2020 Spring Final Exam Questions
A. Please select the correct answer for questions 1-37 (2 pts each). Put down the choice in the box specified for each question in column B.
Example: Which of the following is the satellite of Earth? | B
A. Venus
B. Moon
C. Mars
D. Jupiter
1) Which is the correct sequence in the life cycle of a project? | C
A. Transfer-Concept-Development-Execution
B. Execution-Development-Transfer-Concept
C. Concept-Development-Execution-Transfer
D. None of the above
2) The zero duration of milestones in project planning occurs because milestones: | C
A. Are unpredictable and challenge the Plan Schedule Management process.
B. Occur at random times in the project plans.
C. Represent a moment in time such as a significant project point or event.
D. Represent both significant and insignificant points in the project and are difficult to anticipate.
3) Which tools or techniques will the project manager use for developing the project team? | C
A. Negotiation
B. Roles and responsibilities
C. Recognition and rewards
D. Prizing and promoting
4) What is the total float of the critical path? | B
A. Can be any number
B. Zero or negative
C. Zero or positive
D. Depends on the calendar
5) Which one of the following statements is wrong? | B
A. CMMI tells what needs to be done.
B. CMMI shows exactly how processes should be managed.
C. CMMI is a guide for improvement and development.
D. CMMI is a framework model that defines the key elements for an effective software development process.
6) In a project, total slack measures the: | B
A. Ability to shuffle schedule activities to lessen the duration of the project.
B. Amount of time an activity can be extended or delayed without altering the project finish date.
C. Cost expended to restore order to the project schedule after crashing the schedule.
D. Estimate of the total resources needed for the project after performing a forward pass.
7) Which one of the following is not an advantage of using Waterfall methodology? | D
A. Design errors are captured before any software is written saving time during implementation.
B. It is easy to use and manage.
C. Excellent technical documentation is part of the deliverables.
D. Testing only at the end makes the software more robust.
8) Which software development methodology is depicted in the figure below? | A
A. Spiral software development
B. Agile
C. Capability Maturity Model Integration.
D. Waterfall
9) You are assigned to implement the project control plan. What should you do to ensure the plan is effective and current? | D
A. Perform periodic project performance reviews.
B. Identify quality project standards.
C. Follow ISO 9000 quality standards.
D. Complete the quality control checklist.
10) Agile is focused on _____. | C
A. project realization
B. benefits delivery
C. value delivery
D. style of working
11) Lean uses the idea of work product being “_____” via customer request. | A
A. pulled
B. pushed
C. negotiated
D. changed
12) Which one of the following is true for Scrum? | B
A. Scrum is a complex framework.
B. Scrum teams consist of project manager and stakeholders.
C. The essence of Scrum is a small team of people.
D. Scrum depends on a single delivery at the end of a release cycle.
13) Which of the following activities is part of Sprint Review? | B
A. The Scrum team members answer short questions in 15 minutes.
B. The Scrum team and stakeholders collaborate about what was done in the Sprint.
C. The Scrum team members identify and order the major items that went well and potential improvements.
D. The Scrum Master ensures that the meeting is positive and not about blaming each other.
14) According to the Herzberg's Motivation Hygiene Theory, which of the following is a hygiene factor? | B
A. Achievement
B. Good Working Conditions
C. Recognition
D. Career Advancement
15) Which one of the following is a problem solving model for improvement? | A
A. Plan-Do-Check-Act
B. Review-Risk Analysis-Engineering-Planning
C. Design-Development-Testing-Feedback
D. Plan-Build-Test-Review
16) Which one of the following is false? | C
A. Lean principle pursues perfection by eliminating waste.
B. Agile processes empower product teams.
C. Scrum master acts as the product owner.
D. Kanban methodology prefers visual metrics.
17) How does an Agile project react when the business changes its mind? | C
A. Resists the change
B. Sees it as a fact of life
C. Adopts the change if it is easy to accommodate
D. Re-starts the project.
18) Agile to be successful requires _____? | D
A. on time delivery, according to business priorities
B. communication via chat
C. acceptance that change must be controlled
D. understanding of business requirements and wants
19) You are managing a project to develop a new robot for a mining rescue company. You are currently performing a monitoring and controlling project activity and you have discovered that some of the project work has not been performed according to the plan. If these issues are not fixed before the next customer inspection, your project might be canceled. You have analyzed the situation and you know what corrective actions are required. What should you do first? | B
A. Implement the corrective actions
B. Submit a change request
C. Consult the project sponsor
D. Delay the scheduled customer inspection
20) Your team finished creating the initial version of the risk register during your latest workshop. What is the next thing that you should do? | A
A. Assess the probability of occurrence and the impact for each risk
B. Identify the risk effects and assign a numerical rating to each
C. Review cost planning to ensure that enough risk reserve is available
D. Identify, analyze and plan for newly-arisen risks
21) When does risk monitoring and control occur? | C
A. At project initiation
B. During work performance analysis
C. Throughout the life of the project
D. At project milestones
22) Lessons learned are created and project resources are released in which Process Group? | C
A. Planning
B. Executing
C. Closing
D. Initiating
23) All of the following statements are true about product and project life cycles except | A
A. Generally a product lifecycle is contained within a project lifecycle.
B. A project life cycle is determined by the organization and generally consists of phases that may be sequential or overlapping.
C. A product lifecycle is determined by the organisation and generally consists of sequential phases.
D. Generally a project lifecycle is contained within a product lifecycle.
24) A relationship between two tasks is known as a _____________ . | A
A. Task Dependency
B. Slack Time
C. Critical Path
D. Padding
25) Which of the following is NOT a knowledge area? | B
A. Project Scope Management
B. Project Public Relations Management
C. Project Risk Management
D. Project Cost Management
26) For the network diagram given below, which one is the critical path? | D
A. 1 à 2 à 3 à 6 à 8 à 10
B. 1 à 2 à 3 à 5 à 7 à 9 à 10
C. 1 à 2 à 4 à 7 à 8 à 10
D. 1 à 2 à 4 à 7 à 9 à 10
27) Which of the following is NOT a feature of source code management? | C
A. Backup and Restore
B. Track Changes
C. Sending update notifications
D. Branching and Merging
28) Which of the following statements correctly characterizes pull communication? | B
A. It includes letters, memos, reports, emails, and faxes.
B. It requires recipients to access communication content at their own discretion.
C. It is the most efficient way to ensure a common understanding among all participants.
D. It is primarily used when the volume of information to be transferred is minimal.
29) Projects can be divided into phases to provide better management control. Collectively, what are these phases known as? | C
A. Complete project phase
B. Project life
C. The project life cycle
D. Project cycle
30) Which of the following is correct? | B
A. Centralized version control systems work on a peer-to-peer model
B. Distributed version control systems are faster.
C. Distributed version control systems depend on the access to the server.
D. It is harder to control access on the centralized version control systems.
31) What is the probability of occurrence if the risk rating is 0.56 and the impact if the risk does occur is very high (0.80)? | C
A. 0.45
B. 0.56
C. 0.70
D. 1.36
32) Which of the following is a tool and technique for Estimate Activity Durations? | A
A. Parametric estimating
B. Monte Carlo analysis
C. Alternatives analysis
D. Bottom-up estimating
33) Which one of the following is NOT a required skill for project management? | C
A. Budgeting skills.
B. Negotiation skills.
C. Business development skills.
D. People skills.
34) Your customer calls you on the phone and informs you of a minor change to a requirement on the project. What is the first thing that should be done? | C
A. Analyze the request and its consequences to the project
B. Instruct your engineer to implement this minor change
C. Ask the customer to provide a formal change request
D. Note it in the weekly status report
35) Your pharmaceutical drug manufacturing project is running late and you have deadlines to meet on your project. You want to replace some of the inefficient human resources with more talented human resources to finish the project on time. What risk response strategy is being followed in this context? | D
A. Share
B. Accept
C. Transfer
D. Mitigate
36) Which of the following is wrong? | B
A. Operations and projects are performed by people.
B. Operations and projects are ongoing and repetitive.
C. Operations and projects are constrained by limited resources.
D. Operations and projects are planned, executed, and controlled.
37) Which of the following term is best defined by the statement “The creation of a new codeline from a version in an existing codeline”? | A
A. Branching
B. Merging
C. Codeline
D. Mainline
B. Write down your answers in the cell specified with bold frame for each question for questions 38-43.
38) How many levels are there in CMMI? Write down their names in the increasing order. | 5 | 1)Initial | 2)Managed | 3)Defined | 4)Quantitatively Managed |  | 5)Optimizing
39) List the names of the five process groups. |  | 1)The Scoping Process Group | 2) The Planning Process Group | 3)The Launching Process Group | 4)The Monitoring & Controlling Process Group | 5)The Closing Process Group
40) Write down the names of the three edges of the scope triangle. |  | Time | Cost | Resource Availability
41) List the four ceremonies of Scrum. |  | 1)Sprint Planning | 2)Sprint Demo | 3)Daily Stand-up | 4)Retrospective
42) Fill in the blanks.
_________________ is a schedule contingency for the unexpected. | Management Reserve
_____________ is something the product/project should do/produce or a quality that it must have. | Requirement
____________ is the point where adding more resources will increase task duration. | Crashpoint
In the ___________ project management life cycle model the five process groups are each executed only once. | Linear
Materials such as letters, faxes, which are sent to specific recipients who need to receive the information is a type of ___________ communication. | Push
43) Briefly explain the real key difference between Waterfall and Agile software methodologies. (Hint: It is not about iterations.)
Agile method is flexible(Requirements can be changed) but Waterfall method is not flexible(Requirements cannot be changed).
Agile method is not need project managers because the projects are managed by the entire team, for Waterfall method the process is straightforward, the project managers play key rol for every stage.
Agile method seperates the project development cycle into sprints, waterfall methods divides software development process into distinct phases.
On the Agile Method,tests(reviews) are made after each sprint, on the Waterfall method, test plan is discussed during the test phase.